## Start Here
Wedding Planning Checklist & 12-Month Timeline
Simple Sheets Co. — Excel + Google Sheets
Setup
1. Enter your wedding date at the top. Every task's target date calculates from it.
2. Tick Done as you go. The status column flags anything overdue.
3. Add your own tasks at the bottom; set 'months before' and it slots in.
Conventions
• Yellow cells with blue text are inputs. Type over the sample numbers.
• Black text is a formula. Leave it alone unless you know what you're changing.
• Green text pulls from another tab.
• Works in Excel 2016+ and Google Sheets (File > Import > Upload > Replace). No macros.
For planning and educational use only. Not financial, legal, or tax advice. Every number is an estimate you should verify for your own business.

## Dashboard
Wedding Countdown
Everything on the list, and how close you are.
DAYS TO THE WEDDING | TASKS DONE |  | TASKS LEFT | OVERDUE
239 | 5 |  | 19 | 3
DUE IN NEXT 30 DAYS | WEDDING DATE
2 | 2027-05-15
Progress |  |  |  |  | Status
████████░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░ 21% |  |  |  |  | Done | 5
[5 empty] | Overdue | 3
Next up (not done, soonest first) |  |  |  |  | Upcoming | 16
Book DJ / band |  | 2026-08-14
Choose wedding party |  | 2026-08-14
Order dress / suit |  | 2026-09-13
Book florist |  | 2026-10-14
Book officiant |  | 2026-10-14
Send save-the-dates |  | 2026-11-13

## Checklist
Wedding Checklist
How to use: type your numbers in the yellow cells (blue text). Everything else calculates.
Wedding date (yyyy-mm-dd) | 2027-05-15
Task | Months before | Target date | Done (Y) | Status | Owner | Notes | pending #
Set budget & guest count | 12 | 2026-05-15 | Y | Done
Book venue | 12 | 2026-05-15 | Y | Done
Hire planner (optional) | 11 | 2026-06-14 | Y | Done
Book photographer / videographer | 10 | 2026-07-15 | Y | Done
Book caterer | 10 | 2026-07-15 | Y | Done
Book DJ / band | 9 | 2026-08-14 |  | OVERDUE |  |  | 1
Choose wedding party | 9 | 2026-08-14 |  | OVERDUE |  |  | 2
Order dress / suit | 8 | 2026-09-13 |  | OVERDUE |  |  | 3
Book florist | 7 | 2026-10-14 |  | Due soon |  |  | 4
Book officiant | 7 | 2026-10-14 |  | Due soon |  |  | 5
Send save-the-dates | 6 | 2026-11-13 |  |  |  |  | 6
Book hotel room blocks | 6 | 2026-11-13 |  |  |  |  | 7
Order invitations | 5 | 2026-12-14 |  |  |  |  | 8
Plan honeymoon | 5 | 2026-12-14 |  |  |  |  | 9
Book hair & makeup | 4 | 2027-01-13 |  |  |  |  | 10
Order cake | 4 | 2027-01-13 |  |  |  |  | 11
Buy rings | 4 | 2027-01-13 |  |  |  |  | 12
Mail invitations | 2.5 | 2027-02-28 |  |  |  |  | 13
Finalize menu & tasting | 2 | 2027-03-15 |  |  |  |  | 14
Marriage license (check state timing) | 1 | 2027-04-14 |  |  |  |  | 15
Final headcount to caterer | 0.5 | 2027-04-29 |  |  |  |  | 16
Seating chart | 0.5 | 2027-04-29 |  |  |  |  | 17
Confirm all vendors | 0.25 | 2027-05-07 |  |  |  |  | 18
Pay final balances | 0.1 | 2027-05-11 |  |  |  |  | 19
Tasks done | 5 of 24
Overdue | 3
Days to the wedding | 239
Formulas:
Status = IF([Done (Y)]="Y","Done",IF(DATEVALUE([Target date])<TODAY(),"OVERDUE",IF(DATEVALUE([Target date])-TODAY()<=30,"Due soon","")))
Status = IF([Task]="","",IF([Done (Y)]="Y","Done",IF(DATEVALUE([Target date])<TODAY(),"OVERDUE",IF(DATEVALUE([Target date])-TODAY()<=30,"Due soon",""))))